## Sheet1
Melissa Pawson, Arcata Educational Farm Solar Hot Water Heater, 02/08/10 | [6 empty] | Res | Des | Con | Tes | Inf | Total
Date | Task | Research | Design | Construction | Testing | Infrastructure | 13 | 10 | 30.5 | 2.5 | 31.45 | 87.45 | (time in hours)
2010-01-25 | Went to AEF to check out the infrastructure. |  |  |  |  | 0.5 | 14.87% | 11.44% | 34.88% | 2.859% | 35.96% | 100%
2010-01-25 | emailing to group members |  |  |  |  | 0.25
2010-02-08 | group meeting with Lonny |  |  |  |  | 1
2010-02-10 | CCAT Library, Internet (google scholar) | 2.5
2010-02-12 | research | 2
2010-02-12 | Literature review |  |  |  |  | 1
2010-02-13 | Finishing lit review |  |  |  |  | 2
2010-02-15 | group meeting |  |  |  |  | 1
2010-02-16 | constructing criteria list |  |  |  |  | 2
2010-02-22 | group meeting |  |  |  |  | 1
2010-02-23 | design at farm |  | 1
2010-03-01 | group meeting |  |  |  |  | 1
2010-03-05 | new water tank installation |  |  | 3
2010-03-07 | Timeline on Appropedia | 1
2010-01-25 | Went to AEF to check out the infrastructure. |  |  |  |  | 0.5
2010-01-25 | emailing |  |  |  |  | 0.25
2010-02-07 | Initially began work on timesheet |  |  |  |  | 1
2010-02-08 | group meeting with Lonny |  |  |  |  | 1
2010-02-12 | researching for literature review | 2.5
2010-02-13 | researching for literature review | 3
2010-02-15 | taking measurements |  | 2
2010-02-16 | Working on Criteria List |  |  |  |  | 2
2010-02-22 | group meeting with Maddie Mccann |  |  |  |  | 1
2010-02-23 | Taking Measurements |  | 2
2010-03-01 | Project Budget |  |  |  |  | 0.75
2010-03-02 | Updating Timesheet |  |  |  |  | 1
2010-03-05 | installation of new storage tank |  |  | 1.5
2010-03-08 | group meeting |  | 1
2010-03-10 | Take out leftover copper piping |  |  | 3
2010-03-15 | Designed the Vegetable Washing Station |  | 1
2010-03-16 | wrote vegetable washer proposal to City of Arcata | 2 |  |  |  | 3
2010-03-22 | Call/email Dan Diemer |  | 1
2010-03-22 | group meeting |  | 1
2010-03-24 | farm construction |  |  | 3
2010-03-25 | Constructing solar collector frame |  |  | 3.5
2010-03-26 | Constructing solar collector frame |  |  | 3.5
2010-03-29 | group meeting |  |  |  |  | 1
2010-03-30 | Call/email Dan Diemer |  |  |  |  | 1
2010-04-05 | Organizing group |  |  |  |  | 1
2010-04-07 | Amendments to the design of the vegetable washing station |  | 1
2010-04-10 | Aid 6 rivers in installing solar hot water heater |  |  | 3
2010-04-12 | group meeting |  |  |  |  | 1.2
2010-04-16 | Construction on solar hot water heating system
2010-04-19 | Group meeting |  |  |  |  | 2
2010-04-26 | research testing |  |  | 1 | 1.5
2010-04-29 | research testing |  |  |  | 1
2010-04-30 | Construction on Vegetable washing station |  |  | 4
2010-05-03 | Construction on photovoltaic array |  |  | 2.5
2010-05-05 | Construction on photovoltaic array |  |  | 2.5
2010-05-07 | Making movie and taking final pictures |  |  |  |  | 1
2010-05-08 | Working on Appropedia project page |  |  |  |  | 4
Note on C2: O: This column is for time spent research, defining the opportunity, criteria and constraints.
Note on D2: O: This column is for time spent designing and planning, including time spent acquiring materials.
Note on E2: O: This column is for time spent constructing.
Note on F2: O: This column is for time spent testing your design.
Note on G2: O: This column is for time spent developing documentation and interpretive materials, including posting to Appropedia.