## Sheet1
Deidre Russell, Vertical Vegetable Garden, April 28, 2010 | [6 empty] | Res | Des | Con | Tes | Inf | Total
Date | Task | Research | Design | Construction | Testing | Infrastructure | 19 | 13 | 42 | 24.5 | 45.75 | 144 | (time in hours)
2010-01-29 | Post User Page to Appropedia |  |  |  |  | 1
2010-02-02 | Create Project Page |  |  |  |  | 2
2010-02-03 | Design Project Opportunity Defenition |  | 0.5
2010-02-06 | Post Opportunity Defenition to Appropedia |  |  |  |  | 0.25
2010-02-07 | Fill Out Timesheet #1 and Post to Moodle |  |  |  |  | 0.25
2010-02-08 | Begin Literature Review (1 hour a day Mon-Fri) | 5
2010-02-13 | Post Literature Review Information to Appropedia |  |  |  |  | 3
2010-02-14 | Begin Collecting Re-Usable Material for Project |  |  |  |  | 3
2010-02-17 | Update Project Page Aesthetics |  |  |  |  | 1.5
2010-02-20 | Design Criteria |  | 1
2010-02-22 | Post Criteria to Appropedia |  |  |  |  | 0.25
2010-02-23 | Design Budget |  | 1
2010-02-24 | Post Budget to Appropedia |  |  |  |  | 0.25
2010-02-26 | Research Possible Vegetables for Garden | 2
2010-02-27 | Design Vegetable Layout |  | 1
2010-02-28 | Collect Re-Usable Material for Project |  |  |  |  | 2
2010-02-28 | Research Solar Water Pumps and Prices | 3
2/29/10 | Order Solar Pump |  |  |  |  | 1
2010-03-02 | Fill Out Timesheet #2 and Post to Moodle |  |  |  |  | 0.5
2010-03-04 | Design Garden Structure |  | 3
2010-03-05 | Go to Hardware Store for Materials |  |  |  |  | 3
2010-03-06 | Test Solar Water Pump |  |  |  | 10
2010-03-06 | Visit Solar Stores for Help | 4
2010-03-06 | Design Reservoir Structure |  | 2
2010-03-06 | Design Project Goals Timeline |  |  |  |  | 1
2010-03-07 | Went to Arcata Recycling Center and Purchased Reservoir |  |  |  |  | 1
2010-03-07 | Built Reservoir Frame |  |  | 6
2010-03-07 | Post Project Goals Timeline to Appropedia |  |  |  |  | 0.25
2010-03-12 | Go to Hardware Store for Materials |  |  |  |  | 3
2010-03-12 | Went to Arcata Recycling Center and Purchased Gutters |  |  |  |  | 1
2010-03-13 | Built Garden Shelves |  |  | 8
2010-03-14 | Continue Building Garden Shelves |  |  | 6
2010-03-14 | Brainstorm Design for Irrigation System |  | 2
2010-03-14 | Go to Hardware Store for Materials |  |  |  |  | 3
2010-03-15 | Begin Building Irrigation System |  |  | 5
2010-03-17 | Continue Building Irrigation System |  |  | 4
2010-03-17 | Test Irrigation System |  |  |  | 1
2010-03-18 | Go to Hardware Store for Materials |  |  |  |  | 3
2010-03-19 | Finish Building Irrigation System |  |  | 5
2010-03-19 | Test Irrigation System |  |  |  | 2
2010-03-19 | Adjust Irrigation System Design |  | 2
2010-03-20 | Test Irrigation System |  |  |  | 2
2010-03-20 | Mount System to Frame |  |  | 3
2010-03-21 | Collect Re-Usable Material for Project |  |  |  |  | 3
2010-03-21 | Test System Mechanics and Drainage |  |  |  | 3
2010-03-21 | Update Appropedia Page |  |  |  |  | 2
2010-03-25 | Research Soil Mix | 3
2010-03-26 | Make Soil and Planter Boxes |  |  | 3 |  | 0.5
2010-03-26 | Test Soil With Irrigation System |  |  |  | 1
2010-03-26 | Re-Design Soil Planter Medium |  | 0.5
2010-03-26 | Test New Soil With Irrigation System |  |  |  | 2
2010-03-26 | Update Appropedia Page |  |  |  |  | 3
2010-03-26 | Prep Planters for Plants |  |  | 0.5
2010-03-27 | Install Plants |  |  | 1.5
2010-03-27 | Test Water Up-Take of Installed Plants |  |  |  | 2
2010-03-27 | Update Appropedia Page |  |  |  |  | 2
2010-03-27 | Research Fertilizer Options | 2
2010-03-28 | Monitor Finished System for 1 Week. Day 1 |  |  |  | 0.5
2010-03-31 | Monitor Finished System for 1 Week. Day 4 |  |  |  | 0.5
2010-04-03 | Monitor Finished System for 1 Week. Day 7 |  |  |  | 0.5
2010-04-10 | Update Appropedia Page |  |  |  |  | 3
2010-04-28 | Final Updates of Appropedia Page |  |  |  |  | 2
Note on C2: O: This column is for time spent research, defining the opportunity, criteria and constraints.
Note on D2: O: This column is for time spent designing and planning, including time spent acquiring materials.
Note on E2: O: This column is for time spent constructing.
Note on F2: O: This column is for time spent testing your design.
Note on G2: O: This column is for time spent developing documentation and interpretive materials, including posting to Appropedia.