## Basic Manual Gantt Chart
Spirograph Project Gantt Chart
Task Name | Start Date | End Date | Duration | RP | Start Date in Number Form | 43007 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Section 2 - Problem Analysis | 2017-09-29 | 2017-10-05 | 6
Section 3- Alternative Solutions | 2017-10-05 | 2017-10-12 | 7
Section 4 - Decision | 2017-10-12 | 2017-10-17 | 5
Section 5 - Specification | 2017-10-17 | 2017-11-07 | 21
Practice Presentation | 2017-11-02 | 2017-11-09 | 7
Draft Poster | 2017-11-07 | 2017-11-14 | 7
Final Poster | 2017-11-14 | 2017-11-28 | 14
Final Presentation | 2017-10-05 | 2017-11-16 | 42
Final Documents and Old Edits | 2017-11-27 | 2017-12-01 | 4
Final Appropedia Page | 2017-11-15 | 2017-12-03 | 18
Purchasing Materials | 2017-10-10 | 2017-11-15 | 36
Building Prototypes | 2017-10-10 | 2017-11-15 | 36
Final Construction of Project | 2017-10-10 | 2017-11-15 | 36